## 9. Implementation Plan (MVP → Phase 2) + Backlog Decomposition

Ниже — практический план реализации модуля AI Evidence Validation & Client Concierge Layer с декомпозицией по потокам работ:

- Backend

- Frontend (Client/Internal)

- AI/Prompting

- Infra/DevOps

- QA/UAT

Цель: дать тебе структуру, по которой можно собирать ТЗ + backlog + этапы внедрения, без хаоса и без преждевременного усложнения.

# 9.1. Стратегия реализации (главный принцип)

## 9.1.1. Сначала — скелет orchestration, потом “ум”

Правильный порядок:

- Данные и state machines

- API и orchestration

- UI минимального цикла

- Claude/ChatGPT adapters

- Качество prompt’ов и UX polishing

То есть не начинать с “идеальных prompt’ов”, пока нет устойчивого pipeline.

## 9.1.2. MVP = один рабочий контур end-to-end

Минимальный целевой контур MVP:

Upload evidence → Extract → Analyze (Claude) → Aggregate → Task created → Client sees task → Client asks assistant (ChatGPT) → Client replies/uploads update → Reanalysis → Task resolved

Если этот контур работает стабильно — MVP состоялся.

## 9.1.3. Жесткое разделение фаз

- MVP: рабочая логика и устойчивость

- Phase 2: удобство, ускорение triage, история, debug UI, next-best-actions, advanced conflict handling

# 9.2. Этапы реализации (high-level roadmap)

## Phase 0 — Foundation / Alignment (короткий, но обязательный)

Цель: зафиксировать контракты и архитектурные границы до кодинга.

### Deliverables

- Финализированный документ разделов 1–8 (то, что мы уже собрали)

- Enum list / field naming freeze

- MVP scope freeze

- Acceptance criteria freeze (must-have gate)

### Результат

Команда не “додумывает” статусы/контракты на ходу.

## Phase 1 — Backend Core (Evidence Pipeline + Task Orchestrator)

Цель: поднять backbone без сложного UI.

### Что входит

- DB models / migrations

- state handling

- extraction service integration

- Claude adapter

- persistence + aggregate

- task orchestration

- basic APIs

- audit events

### Результат

Система уже умеет анализировать evidence и создавать/обновлять задачи.

## Phase 2 — Client/Internal UI MVP + ChatGPT Concierge

Цель: дать usable UX для клиента и internal team.

### Что входит

- evidence status badges

- tasks list/detail

- assistant chat (task/question context)

- internal AI analysis panel

- internal task queue

### Результат

Модуль становится продуктовым, а не только backend pipeline.

## Phase 3 — Stabilization / QA / Degraded Mode Hardening

Цель: довести до MVP-ready quality по acceptance criteria.

### Что входит

- retries/timeouts

- fallback templates

- RBAC hardening

- tenant isolation tests

- UAT сценарии

- observability polish

### Результат

Можно показывать/включать в рабочий продукт.

## Phase 4 — Phase 2 Enhancements (после MVP)

- next-best-actions

- analysis history/diff

- AI debug panel

- aggregate conflict tooling

- push updates

- richer internal triage UX

# 9.3. MVP Scope (что точно входит / что не входит)

## 9.3.1. MVP Includes

### Backend

- EvidenceExtraction

- EvidenceAssessmentResult

- ControlEvidenceAggregate

- ClientTask

- basic AssistantMessageLog

- Claude analyze flow

- ChatGPT concierge flow (task/question only)

- Task Orchestrator with dedupe

- state transitions (evidence processing + task)

### APIs

- /extract, /extraction

- /analyze

- /evidence-results

- /recompute-evidence-aggregates

- /evidence-aggregates

- /tasks, /tasks/{id}, /tasks/from-analysis, PATCH /tasks/{id}

- /assistant/chat

### UI

- Evidence AI status badge + summary

- Task list + task detail

- Task-scoped assistant chat

- Question “Ask Assistant”

- Internal evidence AI panel

- Internal task queue (basic)

### Security / Ops

- tenant scoping

- RBAC minimum

- audit events (critical)

- degraded mode fallbacks

## 9.3.2. Explicitly Excluded from MVP (Phase 2)

- Analysis diff view

- Internal AI debug console (full)

- Next Best Actions panel/endpoint (optional)

- Primary evidence selection UI

- Conflict resolution UI

- Websocket/push updates

- Advanced prompt experimentation tooling

- Multi-language response tuning

# 9.4. Backlog Decomposition (по workstreams)

## 9.4.A Backend Workstream (основной)

### BE-01. Data model & migrations (core entities)

Priority: P0
Dependencies: contracts frozen

Tasks

- Create tables/models:

  - evidence_extractions

  - evidence_assessment_results

  - control_evidence_aggregates

  - client_tasks

  - assistant_message_logs

  - (optional) evidence_processing_states

- Add indexes:

  - (tenant_id, assessment_id, control_id)

  - (evidence_file_id, control_id)

  - task status filters

- Add uniqueness/dedupe support fields (task fingerprint)

Acceptance

- migrations apply cleanly

- rollback works

- seed/test fixtures available

### BE-02. Evidence Processing State Machine implementation

Priority: P0
Dependencies: BE-01

Tasks

- Implement EvidenceProcessingState transitions

- Add transition guards

- Add audit event hooks

- Retry counters / failure reason fields

- stale marking logic (minimum manual trigger + prompt/spec change hook placeholder)

Acceptance

- invalid transitions rejected

- transitions logged

- retry behavior bounded

### BE-03. Extraction Service integration

Priority: P0
Dependencies: BE-01/02

Tasks

- Implement service wrapper for extraction

- Parse/store EvidenceExtraction result

- Handle supported formats (at least current targeted file types)

- Normalize extraction output

- Failure handling + error details

- Async job orchestration (queue or background worker)

Acceptance

- extraction success/fail reflected in state machine

- GET /extraction returns status

- no raw parse exceptions leaked to client

### BE-04. ControlExpectationSpec service

Priority: P0
Dependencies: contracts frozen

Tasks

- Load control expectation specs from YAML/JSON

- Schema validation for spec files

- Versioning support

- Service method: get spec by control_id

- Caching

Acceptance

- missing spec returns controlled error

- spec validation fails fast on bad files

- spec version visible in requests/logs (if tracked)

### BE-05. Claude Analyst Adapter + request/response validation

Priority: P0
Dependencies: BE-03, BE-04

Tasks

- Build Claude Analyze Request

- Provider adapter wrapper (timeouts/retries)

- Parse structured output

- Validate EvidenceAssessmentResult schema

- Normalize enums/strings/scores

- Server-side status normalization (threshold check)

- Store raw provider error metadata safely (internal only)

Acceptance

- valid Claude response persists EvidenceAssessmentResult

- invalid JSON -> analysis_failed

- provider/model/prompt_version persisted

### BE-06. Aggregate calculator (ControlEvidenceAggregate)

Priority: P0
Dependencies: BE-05

Tasks

- Implement deterministic aggregation rules

- Recompute single control and batch

- Persist aggregate + source trace (analysis_ids_used)

- Null-safe behavior when no evidence exists

Acceptance

- same inputs => same aggregate

- recompute endpoint updates only target controls

- aggregates readable via API

### BE-07. Task Orchestrator (upsert + state logic)

Priority: P0
Dependencies: BE-05, BE-06

Tasks

- Implement task decision rules (status -> task action)

- Task fingerprint generation

- Upsert logic (no duplicate active tasks)

- Auto-resolve logic on validated aggregate/result

- Reopen logic (optional MVP minimal)

- Reason logging for dismiss/resolve

Acceptance

- duplicate analyses do not create duplicate open tasks

- weak/mismatch create/update tasks

- validated can resolve linked task automatically

### BE-08. Task State Machine + PATCH rules

Priority: P0
Dependencies: BE-07

Tasks

- Enforce allowed transitions by role

- client_user limited to client_replied

- internal/system overrides with reasons

- status change audit events

Acceptance

- invalid transitions rejected

- client cannot set resolved

- audit log entries created

### BE-09. Assistant Context Builder (ChatGPT input)

Priority: P0
Dependencies: BE-07/08 + task/evidence APIs

Tasks

- Build AssistantConversationContext for:

  - task context

  - question context

- Tenant scoping

- Allowed sources filtering

- Response policy injection

- Trim payloads for token control

Acceptance

- context contains only tenant-scoped data

- raw extraction/full evidence not included in customer-service mode

- debug logs/internal preview possible (even if no endpoint yet)

### BE-10. ChatGPT Concierge Adapter

Priority: P0
Dependencies: BE-09

Tasks

- Provider wrapper + retries/timeouts

- Request formatting for structured response

- Schema validation for ChatGPT Concierge Response

- Save AssistantMessageLog

- Route task_suggestion via Task Orchestrator (not direct update)

Acceptance

- task/question chat returns assistant message + steps

- provider failure returns controlled error/fallback path

- no direct task mutation from raw ChatGPT output

### BE-11. API Endpoints (MVP set)

Priority: P0
Dependencies: BE-03..10

Tasks
Implement endpoints from section 5 (MVP list):

- extract/extraction

- analyze

- evidence-results

- recompute aggregates

- evidence-aggregates

- tasks list/detail/patch/from-analysis

- assistant/chat

Acceptance

- response envelope consistent

- RBAC and tenant checks enforced

- error codes match spec

### BE-12. Audit events + observability baseline

Priority: P0
Dependencies: all core services

Tasks

- Emit audit events for key transitions

- Correlation/request IDs in logs

- Structured logs for AI calls (no sensitive leakage)

- Metrics counters (basic):

  - extraction success/fail

  - analysis success/fail

  - task created/resolved

  - assistant provider fail

Acceptance

- critical events visible in logs/audit store

- troubleshooting path exists for failed analyze/chat

### BE-13. Degraded mode & fallback templates

Priority: P0
Dependencies: BE-07, BE-10, BE-11

Tasks

- Claude unavailable behavior (analysis_failed + UI-safe status)

- ChatGPT unavailable fallback task message template

- Null-safe assistant endpoints

- Retry caps / no infinite loops

Acceptance

- AI provider outage does not break core assessment workflow

- client task can still exist with fallback wording

## 9.4.B Frontend Workstream — Client Portal

### FE-C-01. Evidence status badge + AI summary in Evidence Vault

Priority: P0
Dependencies: BE-11 (GET extraction, GET analysis, aggregates)

Tasks

- Add processing status UI

- Add semantic status badge mapping

- Add compact AI summary block

- Add error/failure UI states

- Add stale indicator

Acceptance

- user sees processing and semantic status correctly

- weak/mismatch show clear CTA path

### FE-C-02. Evidence action buttons (Ask / How to Fix / Re-check / Upload Updated)

Priority: P0
Dependencies: FE-C-01 + assistant/task APIs

Tasks

- Contextual action rendering by state

- Button permissions / disabled states

- Wire “Ask Assistant” to task/control/question context

- Wire re-check trigger if enabled

Acceptance

- actions appear correctly by state

- no invalid actions shown during processing/failure states (except allowed retries)

### FE-C-03. Task List view (client)

Priority: P0
Dependencies: GET /tasks

Tasks

- List table/cards

- Filters (open/resolved minimum)

- Status labels mapping

- Click-through to detail

Acceptance

- client sees open tasks and status changes reflected

### FE-C-04. Task Detail view (client)

Priority: P0
Dependencies: GET /tasks/{id}, assistant/chat, patch task

Tasks

- Task header/status

- Message + action steps

- Related evidence panel

- Reply form (“I’ve updated this”)

- task-scoped assistant panel mount point

Acceptance

- client can read task, respond, and ask AI in same screen

### FE-C-05. Task-scoped Assistant Chat Panel

Priority: P0
Dependencies: POST /assistant/chat

Tasks

- Chat UI (minimal)

- context badge (Task/Control/Question)

- loading/error states

- render structured steps

- fallback message on assistant unavailable

Acceptance

- assistant returns contextual answers

- UI survives provider errors gracefully

### FE-C-06. Questionnaire “Ask Assistant” trigger + help panel

Priority: P0
Dependencies: POST /assistant/chat (question mode)

Tasks

- Add trigger per question

- Modal/side panel

- Render simple explanation + examples

- optional “copy guidance”

Acceptance

- user can ask about a question and get contextual help

### FE-C-07. Dashboard widget (optional MVP / recommended)

Priority: P1
Dependencies: tasks + aggregates endpoints

Tasks

- Open tasks count

- weak evidence count

- CTA links

Acceptance

- widget reflects current data and links to task list

## 9.4.C Frontend Workstream — Internal Portal

### FE-I-01. Internal AI Analysis Panel (evidence review screen)

Priority: P0
Dependencies: evidence-results API

Tasks

- Render Claude analysis fields:

  - status/scores/findings/summary

- Collapsible metadata (provider/model/prompt_version)

- Error/failed analysis display

Acceptance

- internal user can inspect AI analysis details without raw logs

### FE-I-02. Re-run Analysis action (internal)

Priority: P0
Dependencies: /analyze

Tasks

- Add action button

- show pending/analyzing states

- confirmation/force reanalyze toggle (optional)

- refresh results after completion (polling)

Acceptance

- internal user can trigger reanalysis and see updated state

### FE-I-03. Internal Task Queue (basic)

Priority: P0
Dependencies: GET /tasks, PATCH /tasks/{id}

Tasks

- Table with filters (status minimum)

- quick actions: resolve/dismiss/reopen (if enabled)

- reason capture modal

- task detail navigation

Acceptance

- internal team can triage AI tasks and apply manual overrides

### FE-I-04. Control-level aggregate card (optional MVP, recommended P1)

Priority: P1
Dependencies: GET /evidence-aggregates

Tasks

- Display aggregate status/score/evidence count on control detail screen

Acceptance

- internal can see control-level evidence quality summary

## 9.4.D AI / Prompting Workstream (Claude + ChatGPT)

### AI-01. Prompt specification package (versioned)

Priority: P0
Dependencies: data contracts final

Tasks

- Claude evidence analysis prompt (claude-evidence-v1.0)

- ChatGPT concierge prompt (concierge-v1.0)

- output schema instructions (strict)

- examples for common statuses

- refusal/limits guidance for ChatGPT (no legal certainty)

Acceptance

- prompts versioned in repo/config

- prompt_version injected into outputs

### AI-02. Claude calibration set (evaluation samples)

Priority: P0
Dependencies: AI-01 + sample docs/specs

Tasks

- Build small labeled set (10–20 samples initially):

  - validated

  - weak

  - mismatch

  - unreadable

- Expected outputs for schema/status

- Manual review sheet for prompt tuning

Acceptance

- prompt iterations measured against same sample set

- status consistency improves and is trackable

### AI-03. ChatGPT concierge response style/copy constraints

Priority: P0
Dependencies: AI-01

Tasks

- Define response policy

- define forbidden phrases list

- ensure plain-language style with actionable steps

- task vs question context examples

Acceptance

- UAT responses are understandable and non-legalistic

- forbidden certainty claims suppressed

### AI-04. Fallback templates (non-LLM)

Priority: P0
Dependencies: BE degraded mode

Tasks

- Task message fallback templates by task_type

- Assistant unavailable message templates

- Analysis failed user-facing copy templates

Acceptance

- product remains usable when provider down

### AI-05. Phase 2 evaluation harness (later)

Priority: P2
Tasks

- compare prompt versions

- log-based QA samples

- regression checks

## 9.4.E Infra / DevOps Workstream

### INF-01. Secrets/config management for providers

Priority: P0

Tasks

- Store Claude + OpenAI creds securely

- env var config per environment

- timeouts/retries configurable

- provider feature flags (enable/disable)

Acceptance

- providers can be toggled without code changes

- no secrets in logs/client responses

### INF-02. Async job execution (extraction/analyze)

Priority: P0

Tasks

- queue/worker setup (or existing background jobs)

- job status persistence

- retry/backoff config

- dead-letter/manual retry strategy (minimum logging if no DLQ yet)

Acceptance

- long-running jobs don’t block API

- retries bounded and observable

### INF-03. Monitoring & alerts (minimum)

Priority: P1

Tasks

- basic metrics dashboard

- alert on repeated provider failures / job backlog growth

- error rate visibility for analyze/chat endpoints

Acceptance

- team can detect outage/degradation quickly

### INF-04. Feature flags / rollout controls

Priority: P1

Tasks

- enable by tenant / assessment / user role

- separate flags for:

  - Claude analysis

  - ChatGPT concierge

  - task auto-generation

Acceptance

- gradual rollout possible

- easy kill switch for one layer

## 9.4.F QA / UAT Workstream

### QA-01. Schema and contract validation tests

Priority: P0

Tasks

- tests for EvidenceAssessmentResult validation

- tests for ChatGPT Concierge Response validation

- enum/range validation tests

- malformed payload tests

Acceptance

- invalid payloads rejected predictably

### QA-02. State machine tests (evidence/task)

Priority: P0

Tasks

- valid transitions

- invalid transitions

- role-based transition restrictions

- retry/fail behavior

- stale handling basics

Acceptance

- state transitions deterministic and protected

### QA-03. E2E integration tests (backend)

Priority: P0

Tasks

- Upload → extract → analyze → aggregate → task path

- reupload/reanalysis resolution path

- provider error paths

- tenant access denial paths

Acceptance

- core MVP flow passes automated integration test set

### QA-04. UI/UAT test scripts

Priority: P0

Tasks

- manual scripts for client flows

- manual scripts for internal triage flows

- degraded mode scripts

- screenshots/evidence checklist for acceptance

Acceptance

- AC scenarios from section 8 covered and documented

# 9.5. Suggested Sprint Plan (practical sequencing)

Ниже — не “идеальная Agile теория”, а рабочая последовательность.

## Sprint 1 — Backend skeleton + contracts in code

Focus: data + states + extraction/analyze backbone (без UI polish)

### Target outcomes

- BE-01, BE-02, BE-04, skeleton of BE-05

- API stubs for core endpoints

- contract schemas in code

- basic audit events

### Demo

- Mocked or partial analyze flow persisting placeholder EvidenceAssessmentResult

## Sprint 2 — Claude pipeline + aggregate + task orchestration

Focus: real backend MVP loop

### Target outcomes

- BE-03, BE-05, BE-06, BE-07, BE-08, BE-11 (core subset)

- dedupe logic

- degraded mode basics for Claude

### Demo

- Upload evidence → analyze → aggregate → task auto-created

## Sprint 3 — Client UI MVP + internal AI panel

Focus: make it usable

### Target outcomes

- FE-C-01..04

- FE-I-01..03

- BE endpoint refinements for UI needs

### Demo

- client sees evidence statuses + tasks

- internal sees AI analysis and can re-run

## Sprint 4 — ChatGPT Concierge + stabilization

Focus: assistant value + failure hardening

### Target outcomes

- BE-09, BE-10, BE-13

- FE-C-05, FE-C-06

- AI-01..04

- QA-01..04 pass on MVP scope

### Demo

- task-scoped and question-scoped assistant live

- provider failure fallback verified

## Sprint 5 — MVP hardening / UAT / rollout controls

Focus: readiness for production enablement

### Target outcomes

- RBAC/tenant security hardening

- observability improvements

- feature flags

- UAT evidence package against ACs

### Demo / Exit criteria

- MVP acceptance gate from section 8 passed

# 9.6. Dependencies Map (critical path)

## Critical Path (must happen in order)

- Contracts frozen

- DB models + state machines

- Extraction + Claude adapter

- Aggregate + Task Orchestrator

- Core APIs

- Client task UI + evidence status UI

- Assistant context builder + ChatGPT adapter

- Assistant UI

- QA/UAT + degraded mode hardening

If команда начнет с chat UI/prompt polishing раньше пунктов 2–5 — будет хаос.

# 9.7. Implementation Risks + Mitigations (очень важно)

## Risk 1 — “LLM answers everywhere, no structure”

Проблема: команда начнет хранить free-text и парсить его потом
Mitigation: strict JSON schema validation + reject invalid outputs (BE-05/BE-10)

## Risk 2 — Duplicated tasks flood client

Проблема: каждый reanalysis создает новую задачу
Mitigation: task fingerprint + upsert rules (BE-07) + state machine tests (QA-02)

## Risk 3 — ChatGPT starts acting as compliance authority

Проблема: опасный UX/юридические формулировки
Mitigation: AssistantConversationContext.response_policy, forbidden phrase checks, fallback copy standards (AI-03 + BE-10)

## Risk 4 — Cross-tenant leakage

Проблема: критический security failure
Mitigation: tenant-scoped query layer in Context Builder + object-level checks + negative tests (BE-09 + QA-03)

## Risk 5 — Provider outages break workflow

Проблема: AI outage = product outage
Mitigation: degraded mode, fallback templates, feature flags, bounded retries (BE-13, INF-04)

## Risk 6 — UI confusion between analysis and assistant advice

Проблема: клиент не понимает, что является статусом, а что рекомендацией
Mitigation: separate UI blocks/badges/cards (FE-C-01, FE-C-04, copy standards)

# 9.8. Team Roles / Ownership (рекомендуемая раскладка)

## Backend Engineer (Lead on MVP backbone)

Ведет:

- BE-01..13 (основная часть)

- API contracts

- state machines

- orchestration

## Frontend Engineer (Client/Internal)

Ведет:

- FE-C-01..06

- FE-I-01..03

- UX state mapping

## AI/Prompt Engineer (или backend+product совместно)

Ведет:

- AI-01..04

- calibration set

- response policy tuning

## DevOps/Infra Engineer

Ведет:

- INF-01..04

- worker/queue/config/flags

- monitoring basics

## QA / Product QA

Ведет:

- QA-01..04

- UAT scripts

- AC evidence package

Если команда маленькая, backend lead + frontend lead могут закрыть большую часть, но state machine + contracts + degraded mode нельзя “оставить на потом”.

# 9.9. Definition of Done per backlog item (единый шаблон)

Чтобы держать дисциплину, для каждого item фиксировать DoD:

- Code complete

- Tests added (unit/integration where applicable)

- RBAC/tenant checks implemented (if API/UI touches data)

- Audit/logging added (if state-changing)

- Error handling + degraded behavior defined

- Docs/API schema updated

- Demo scenario executed

Это резко снизит риск “формально сделали, но в продукте не работает”.

# 9.10. MVP Exit Package (что подготовить перед включением)

Перед включением модуля в рабочую среду подготовить пакет:

## 1) Technical

- миграции

- env config docs

- feature flags defaults

- endpoint docs

- rollback plan

## 2) QA/UAT

- checklist по AC (section 8)

- скриншоты ключевых flows

- API examples success/failure

- degraded mode verification evidence

## 3) Product/Operations

- internal SOP: как triage AI tasks

- fallback handling SOP при provider outage

- короткая инструкция для support/internal users

# 9.11. Phase 2 Backlog (после MVP)

## P2-01. Next Best Actions engine + UI

- endpoint /assistant/next-best-actions

- dashboard panel

- links to tasks/controls

## P2-02. Analysis History + Diff

- internal history table

- compare two analyses

- prompt-version comparison

## P2-03. AI Debug Console (internal)

- request/response payloads (sanitized)

- validation results

- timings / retries

## P2-04. Aggregate conflict workflow

- conflict state UX

- manual primary evidence selection

- internal resolution actions

## P2-05. Rollout & quality analytics

- provider cost/latency metrics

- task conversion metrics (open → resolved)

- false-positive tracking

## P2-06. Push status updates

- websocket/SSE for processing/analyze updates

# 9.12. Итог раздела (фиксируем)

Правильная реализация этого модуля — это не “подключить 2 LLM”, а собрать управляемый продуктовый контур в таком порядке:

- Contracts + state machines

- Backend orchestration

- Deterministic aggregate + task logic

- UI точек действия

- ChatGPT concierge

- Security + degraded mode + QA hardening

Именно этот порядок даст тебе возможность быстро завершить архитектуру правильно, без расползания scope и без дорогих переделок позже.